## Sheet1
Task | Priority | Description | Assignee | Size | Status | Progress | Deliverables
Phase 0 [Due October 13th]
UML Diagrams | High | Class Diagrams Database Diagrams Server Diagrams Interaction Diagrams | Dennis, James | L | Completed | 100% | Draw.io Diagrams
Project Proposal | High | Summarization of all plans | Dennis, James, Jared | L | Completed | 100% | PDF Document
Screen Designs | High | Basic and Advanced Screen Designs Login Screen Home Screen Visualization Screen Customization Screen TBD Screens | Jared | XL | Completed | 100% | PNG or FIGMA
Server Research | Medium | Gain an understanding of how to setup and host a database for devices on a different network to connect to it. Should figure out which technolgies to use and what hardware will be required. Some thought should also be put into security measures in order to keep the server and data safe. Also investigate alternative methods such as using free database hosting services. Construct Pros and Cons | Dennis | L | Completed | 100% | DENNIS
Digitalization of Plans | Medium | Finish this Spreadsheet | James | M | Completed | 100% | This sheet
Phase 1 [Due October 20th]
Assembling Basic Screens | Medium | Implementation of the basic screen designs, should include the features: Dialogs and Pickers, Screen Navigation, and Snack Bars | Jared | XXL | Not started | 0% | Flutter/Dart Files
Adding Functionality to Screens | Medium | Implement the functionality for all buttons, dialogs, menus, ect. Should allow users to add expenses to budget | James, Jared | XL | Not started | 0% | Flutter/Dart Files
Setting up Database Server | High | Use the knowledge gained during the server research portion to setup the database server. Should be tested and ready to be used by and device | Dennis | XL | Not started | 0% | A working database server
Writing Basic SQL Code | High | Write the SQL tables that will store the basic expenses information | Dennis, James | S | Not started | 0% | SQL Code
Connect Client to Server | High | Connect the client app to the server. Test that expenses reported are sent to the central server | Dennis, James | M | Not started | 0% | Flutter/Dart Files
Phase 2 [Due November 3rd]
Advanced SQL Tables | High | Write more advanced SQL tables to allow for user accounts aswell as more complex expense reports including the categorization of expenses, dates, author, ect | James | L | Not started | 0% | SQL Code
Advanced Data input | Medium | Implement features to allow for more complex expense reporting to conform to the new SQL tables | James, Jared | L | Not started | 0% | Flutter/Dart Files
User Accounts | High | Allow for the creation of user accounts, implement the screen required aswell as the backend communication. | Dennis, Jared | L | Not started | 0% | Flutter/Dart Files
Setting Fonts | Low | Modify all app fonts to replace defaults with pretty fonts | Dennis, Jared | M | Not started | 0% | Flutter/Dart Files
Setting Colours | Low | Modify screen colours to match a consistent theme | Dennis, Jared | M | Not started | 0% | Flutter/Dart Files
Setting Shapes | Low | Modify all screen widgets to have shapes that better conform to their purpose | Dennis, Jared | M | Not started | 0% | Flutter/Dart Files
Notifications | Medium | Add ability for push notifications such as ones to report when new expenses are added or a reminder at the end of each day to report any expenses the user might have forgotten about | James | M | Not started | 0% | Flutter/Dart Files
Phase 3 [Due November 15th]
Data Visualization | Medium | Allow for basic visualization of data. For this iteration just focus on adding simple charts such as a pie chart and line graph for totals | Jared | M | Not started | 0% | Flutter/Dart Files
Export Data Features | Medium | Allow for the exportation of the data in tables to excel and/or sheets | Dennis | M | Not started | 0% | Flutter/Dart Files
UI Customization | Medium | Allow for users to customize their app experience with different colour themes. Currently just light and dark mode | James | M | Not started | 0% | Flutter/Dart Files
Race Conditions | Low | Add preventative measures to the server to prevent race conditions | James, Dennis | M | Not started | 0% | Server/SQL Code
Phase 4 [Due November 29th]
Advanced Data Visualization | Medium | Add more visualization options such as multi line graphs covering the different categories of expenses, bar graphs comparing the monthly limits to the current list of expenses, and treemaps | Jared | L | Not started | 0% | Flutter/Dart Files
Monthly Reports | Medium | Add the ability to enable monthly reports to be sent by email to all collaborators, these reports should include an exported version of the monthly expenses aswell as and trends occuring in the data | Dennis | L | Not started | 0% | Flutter/Dart Files
Monthly Limits | Medium | Add the ability to set monthly limits/goals to each cateogory of expenses | James | M | Not started | 0% | Flutter/Dart Files
Phase 5 BONUS [Due December 2nd]
Data Encryption | High | Encrypt all data transfers between client and server aswell as encrypt user data on the server | Dennis, James | L | Not started | 0% | Server/SQL Code
Animations | Low | Add any animations where seen fit to improve the flow of the app | Jared | L | Not started | 0% | Flutter/Dart Files
Code Polishing | Medium | Go over the entire code base looking for any ways to improve the efficency and readability of the code. | Dennis, James, Jared | L | Not started | 0% | Code Base